## Risk Management
| Process Name |  | Purpose
| Risk Management |  | To identify risks and drawing up plans to minimise their effect on a project
Entry Criteria |  | Controls |  | Exit Criteria
T1 | A reviewed task/project | T5 | Past experiences from experienced developers | T8 | A list of risks that must be monitored have been created
|  | T5 | Company standards and formalities | T8 | All members of the team have agreed on the risks
Inputs |  | Tasks |  | Outputs
T1 | A thoroughly defined task/project | T1 | Create a list of potential risks | T8 | A list of risks that must be monitored throughout the lifespan of the project
|  | T2 | Identify a potential risks
|  | T3 | Create a prioritized list of risks
|  | T4 | Select and analzye a single risk
|  | T5 | Evaluate and rank the risk based on its severity
|  | T6 | Treat the risk by conjuring up a plan on how the risk can be delt with
|  | T7 | Repeat T4 -> T6 unitl all risks have been analyzed
|  | T8 | Monitor and review the risks outlined throughout the lifespan of the project
Metrics |  | Roles |  | Issues
T1 | Number of risks identified | T1->T8 | Project Manager | T1 | Uncotrollable events such as natural disasters
T8 | Number of risks that occurred |  | Risk Manager
T5 | Number of risks that occurred |  | Software Engineers
T8 | Cost of risk management
T1 | Number of risks that were not identified

## Reviews
| Process Name |  | Reviews
| Purpose |  | To ensure quality has been maintained throughtout a piece of work/task/project
Entry Criteria |  | Controls |  | Exit Criteria
T1 | A task that has been makred for review | T4 | Company Product Standards | T5 | A list of issues that must be resolved
|  |  |  | T5 | All members of the team have agreed on the issues needing to be fixed
Inputs |  | Tasks |  | Outputs
T1 | A review team has been put in place | T1 | The author/creator of the work should walk thorugh the work being reviewed | T8 | A list of issues that must be monitored throughout the lifespan of the project
T2 | A time and place for reviews has been put into place | T2 | Assign a member to chair the review
T3 | Documents/Finished work to review | T3 | Assign a member to record all the decsision and actions to be taken
|  | T4 | Once the creator of the work has finished his walk through, the issues and problems raised must be addressed
|  | T5 | A follow up check should take place after the meeting to assure that the issues have been resolved
Metrics |  | Roles |  | Issues
| Number of issues identified | T1 | Software Developer(s)
| Number of issues that were resolved | T1 | Review Leader
| Number of risks that were not identified | T2 | Review Chair
| Cost of issues | T3 | Review Minute-taker
Time needed to resolve the issues